## NPV Rule
NPV RULE FOR CAPITAL BUDGETING
Choose a project if it costs less than the PV of its cash flows. More generally:
take a project if its Net Present Value is positive.
EXAMPLE
Interest rate | 10%
Year | 0 | 1 | 2 | 3
Cash flow | -600 | 200 | 200 | 500
PV factor | 100% | 90.91% | 82.64% | 75.13%
PV of cash flow | -600 | 181.8182 | 165.2893 | 375.6574
Cumulative PV | -600 | -418.1818 | -252.8926 | 122.7648
Net Present Value | 122.7648
Investors would have to invest 123 more (a total of 723) to get the cash flows of 200, 200,
and 500 at an interest rate of 10%. Therefore the project has a value of 123 for investors.
The interest rate is called the cost of capital, because it is the opportunity cost of funds - the
rate investors can earn on alternative investments.

## IRR Rule
IRR RULE
For a standard project, | NPV > 0 | if and only if | IRR > Cost of Capital
IRR Rule: Choose a project |  | if and only if | IRR > Cost of Capital
Standard means
- cash outflows occur in early years and cash inflows in later years.
- the alternative to the project is the status quo.

## Multiple
NONSTANDARD PROJECTS MAY HAVE MORE THAN ONE INTERNAL RATE OF RETURN
Cost of capital | 12%
Year | 0 | 1 | 2
Net cash flow | -400000 | 960000 | -572000
PV factor | 100% | 89.29% | 79.72%
PV of net cash flow | -400000 | 857142.8571 | -455994.898
Cumulative PV | -400000 | 457142.8571 | 1147.9592
Net present value | 1147.9592
IRR (Internal Rate of Return) | 10%
For this project, varying the initial guess in the IRR function can cause the IRR to change.
This is a good project (positive NPV), but you can't tell it from the IRR function. The following
chart shows that there are two break-even costs of capital or IRR's. The NPV is positive at the
actual cost of capital (12%), so it is a good project.

## Multiple-chart
Year | 0 | 1 | 2
Net cash flow | -400000 | 960000 | -572000
Discount Rate | NPV
2% | -8612.0723
4% | -5769.2308
6% | -3417.5863
8% | -1508.9163
10% | 0
12% | 1147.9592
14% | 1969.8369
16% | 2497.0273
18% | 2757.8282
20% | 2777.7778
22% | 2579.9516
24% | 2185.2237
26% | 1612.4969
28% | 878.9062
30% | 0
32% | -1010.101
34% | -2138.5609
36% | -3373.7024
38% | -4704.8939
40% | -6122.449

## Exclusive
AN EXAMPLE OF MUTUALLY EXCLUSIVE PROJECTS
Cost of capital | 10%
|  | Year | 0 | 1
Project A |  | Cash flow | -10000 | 20000
|  | PV factor | 100% | 90.91%
|  | PV of cash flow | -10000 | 18181.8182
|  | NPV | 8181.8182
|  | IRR | 100%
Project B |  | Cash flow | -20000 | 35000
|  | PV factor | 100% | 90.91%
|  | PV of cash flow | -20000 | 31818.1818
|  | NPV | 11818.1818
|  | IRR | 75%
Project B is best, even though its IRR is lower.

## Incremental
PROJECTS CAN BE VALUED ON AN INCREMENTAL BASIS
Cost of capital | 10%
|  | Year | 0 | 1
Project A |  | Cash flow | -10000 | 20000
|  | PV factor | 100% | 90.91%
|  | PV of cash flow | -10000 | 18181.8182
|  | NPV | 8181.8182
Project B-A |  | Cash flow | -10000 | 15000
|  | PV factor | 100% | 90.91%
|  | PV of cash flow | -10000 | 13636.3636
|  | NPV | 3636.3636
Project B has a positive NPV relative to A (on an incremental basis) so should be taken.